## Weekly Gantt Chart Template
WEEKLY GANTT CHART TEMPLATE
|  | Improve School Attendance Project |  |  |  |  | John Smith (Principal) | [6 empty] | 2020-05-03 |  |  |  |  | 2020-08-16
|  | PROJECT NAME |  |  |  |  | OWNER | [6 empty] | START DATE |  |  |  |  | END DATE
Project Description | Task ID | Task Name | Start | End | Resources | WK01 | WK02 | WK03 | WK04 | WK05 | WK06 | WK07 | WK08 | WK09 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17
This project was initiated to improve the attendance of students at all level from 80% to 95% within a one-month period. |  |  | Week | Week
| 01 | Objective Setting | WK02 | WK08 | bar: OWNER WK02 to OWNER WK08
| 01.01 | Define Objectives | WK02 | WK04 | bar: OWNER WK02 to OWNER WK04
| 01.02 | Approve Objectives | WK05 | WK05 | bar: OWNER WK05
| 01.03 | Disseminate Objectives | WK06 | WK08 | bar: OWNER WK06 to OWNER WK08
| 02 | Monitoring / Reporting | WK09 | WK12 | bar: START DATE WK09 to START DATE WK12
| 02.01 | 1st Week | WK09 | WK09 | bar: START DATE WK09
| 02.02 | 2nd Week | WK10 | WK10 | bar: START DATE WK10
| 02.03 | 3rd Week | WK11 | WK11 | bar: START DATE WK11
| 02.04 | 4th Week | WK12 | WK12 | bar: START DATE WK12
| 03 | Weekly Assessment | WK10 | WK13 | bar: START DATE WK10 to START DATE WK13
Remarks | 03.01 | 1st Week | WK10 | WK10 | bar: START DATE WK10
Weekly monitoring shall be done to check if the objectives are being achieved. Improvement on the action plans shall be enhance along the way. | 03.02 | 2nd Week | WK11 | WK11 | bar: START DATE WK11
| 03.03 | 3rd Week | WK12 | WK12 | bar: START DATE WK12
| 03.04 | 4th Week | WK13 | WK13 | bar: START DATE WK13
| 04 | Final Assessment | WK14 | WK16 | bar: END DATE WK14 to END DATE WK16

## ©
© TemplateLab.com