## Network Diagram
NETWORK DIAGRAM
Activity | Predecessor | Duration
A |  | 6
B | A | 2
C | A | 40
D | B | 20
E | B | 9
F | D,E | 4
G | C,E | 15
H | F,G | 3
Start
End

## WBS
WORK BREAKDOWN STRUCTURE - NETWORK DIAGRAM
WBS | Activity name | Activity description | Predecessor activities | Predecessor lead or lag | Successor activities | Relationship to successors | Successor lead or lag | Type of resources required | Resource skill requirements | Number of resources required | Activity assumptions/ constraints
1.0.0.0
1.1.0.0
1.1.1.0
1.1.1.1
1.1.1.2
1.1.1.3
2.0.0.0

## WBS Diagram
WORK BREAKDOWN STRUCTURE DIAGRAM TEMPLATE
PROJECT TITLE |  |  | COMPANY NAME
PROJECT MANAGER |  |  | DATE
PROJECT
PROJECT TITLE
PHASE
| PROJECT PREP | PLANNING | DEVELOPMENT | FINAL PREP | RELEASE
TASK
| Solution Vision | Cost Analysis | Change Management | System Testing | Activate
| Design and Staffing | Risk Assessment | Operations | Stress Testing | Closing Analysis
| Other Task | Technology | Beta Testing | Release Prep | Other Task
| Other Task | Training | Other Task | Other Task | Other Task
| Other Task | Other Task | Other Task | Other Task | Other Task
| Other Task | Other Task | Other Task | Other Task | Other Task
| Other Task | Other Task | Other Task | Other Task | Other Task

## Activity List
ACTIVITY LIST - ACTIVITY ATTRIBUTES
WBS | Level | Deliverable | Work package | Activity | Task | Dependency | Activity sequence | Level of Effort (Hrs) | Responsible | Est Confidence
1.0.0.0 | 1
1.1.0.0 | 2
1.1.1.0 | 3 |  |  | Act 1
1.1.1.1 | 4 |  |  |  | Task 1 | None | 1 | 3 |  | High
1.1.1.2 | 4 |  |  |  | Task 2 |  | 2 | 1 |  | High
1.1.1.3 | 4 |  |  |  | Task 3 |  | 3 | 1 |  | Med
2.0.0.0 | 1 |  |  | Act 2 |  |  | 4 | 6 |  | Low